## Project Schedule
Project Title: JIGAWA EXECUTION PLAN SCHEDULE
Activities/Tasks | Action Needed | Duration | Precursor | Sequence | Schedule (in days) | Resources | Budget
Pre-Kickoff Activities
Payment of acceptance and Documentation fee | Raise payment with finance, | 3 | Award Letter, Mgt. Approval of acceptance fee and documentation fees | 1 | 0 | PM, MGT | 97100000
Review and execute contract agreement | MGT and company Secretary Flight Ticket, and allowance | 3 | Award Letter, Payment of acceptance and Documentation fee | 2 | 0 | PM, MGT | 3000000
Source for project office, accomodation and ware house | PM should get price from agent | 10 | Contract Execution | 2 |  | Agent, PM | 0
Project Execution plan | Preparation of Project execution plan, Reporting and monitoring structure | 5 | Contract Document, Go-by | 3 | 0 | P & RE Unit, MGT | 0
Engage sub-contractors and prepare sub contractor aggreements | PM, legal to develop contract agreement | 10 | Contract, scope of work for sub-contractors | 3 |  | PM, Legal, HR, Management | 0
Submission of Budget | Develop and review budget with execution team | 10 | Project Execution Plan | 3 |  | P & RE Unit, MGT | 0
Prepare PO's for long lead items | Material take off, validate pricing and term of contract with vendors (All in-one, BESS) | 5 | Contract Execution, Price Validation | 3 |  | PM, Finance, MGT | 0
Schedule high level visit to Dubai and China | Management to visit OEM in Dubai and visit Onyx and ATESS factory in China | 7 | DDQ, Invitation letters from parties to be visited | 3 |  | Flight Tickets | 34990000
Get and submit Project Performance Bond | Finance to approach bank with executed contract | 7 | Signed Contract Agreement | 3 |  | PM, Finance | 20000000
Get and submit of APG bond for 30% mobilization | Finance to approach bank with executed contract | 3 | Signed Contract Agreement | 3 |  | PM, Finance | 11600000
Internal project Kickoff meeting | Review execution plan, schedule, budget, Resource, risk Management and operational rediness | 1 | Subcontractors, Approved PEP, Schedule, and Budget. Submission of PB and APG | 4 | 0 | PMT, Sub-contractor, MGT | 300000
Client project Kickoff meeting | project meeting with Client, request a date for site handover | 1 | Internal Kickoff | 5 | 0 | PMT, Client, MGT | 2000000
Mobilization - Submission of of 30% invoice for Lot-1 and Lot-2 | Finance department to prepare 30% invoicess for Lot-1 And Lot 2 Projects, PMT to validate invoice with ministry before submission | 5 | Signed Agreement, Submission of pereformance bond and APG, Project kick off | 6 | 0 | PM, Finance | 0
Payment of 30% Mobilization | Finance confirms payment from Client | 26 | Submission of invoice | 7 | 0 | Client, Finance | 0
Post Kick-off Activities
Release purchase orders for long lead items (All in one and BESS) | Have both parties execute PO for All-in-One & BESS (65 days delivery) | 2 | Pre approved PO | 1 | 2 | PM, Finance | 0
LC and Payment for All-in-One Streetlight and BESS |  | 4 | PO, Payment to OEM, Inspector | 2 | 7 | PM, Finance | 3964120000
Pay for office, accomodation and ware house | Hire office support team, security and drivers and others | 2 | Approved Budget, Mobilization | 3 | 11 | Furniture, consumables, PPE, Printer etc | 19000000
Procurement of 2No Project Vehicle | Procure a new Toyota hilux with Automatic drive of 2021 | 2 | Approved Budget, Mobilization | 3 |  | PM, Admin, MGT | 150000000
Site Hand-over & Community Notification | The client and IESL team will travel to all L.G.A to hand over all All-in-One sites and Mini-Grid sites. We will discuss technical specification of poles head and paining of poles. The client representative will inform the chief of the L.G.A of the up coming work. | 3 | Sub contractor, Confirmation of dates from client | 3 |  | Execution team, Client | 0
Mobilize sub-contractors | Pay sub contractor mobilization fees | 4 | Site Handing over | 3 |  | PE, PM, Finance | 10000000
Kick-off Meeting and on-boarding of sub-contractors | PMT to review scope, quality control, timeline and HSE with sub contractors | 1 | Aproved Budget | 4 | 12 | Execution team, HSE Mgr, QAQC Mgr | 1000000
Detailed Survey and Risk identification for Solar All-in-One Streetlight All the sites | Re-visit each site location in each L.G.A, to have a detailed asessment of the existing streetligh poles and foundation intergrity, and develop a plan on how to correct anomalis and modifypole heads | 9 | project vehicles, cameras | 5 | 23 | Execution team, sub contractors | 0
Detailed Survey for Solar Micro-Grid. | Survey of the Mini-Grid physical locations and production of survey Plans | 9 | Surveyor, site handover | 5 |  | Execution team, sub contractors | 1600000
Traffic Management, and material handling Plan | Develop and implement a traffic management and material plan to minimize disruptions and ensure worker and public safety. | 9 | Site Handing over | 5 |  | Execution team, sub contractors | 0
Materials Take off | Prepare list of all materials needed for light pole modification and installation including painting and alignment | 9 | Site handover | 5 |  | Execution team, sub contractors | 0
Comprehensive Site Survey Report | Data from all site visits and survey | 3 | Detail survey | 6 | 26 | PMT | 0
Risk Management Workshop | Organise workshop | 2 | Comprehensive Site Survey Report | 7 | 29 | PMT, QAQC, HSE, Facilitator, MGT | 2000000
Materials market survey, planing and costing | Travel to Kano for market survey, availability of materials | 2 | Material takeoff | 8 | 32 | PMT | 0
Procurement of Toolbox & Ladders | Safety barriers, Warning tape, Work in progress" signs, high-visibility vest, hand gloves, safety goggles, helmet, safety boots, Insulated tools, Multimeter, Mechanical and Electrical toolbox | 3 | Approved Budget, Fund release | 8 |  | PMT, Finance | 2100000
Procurement of perimeter wire fence materials for 4 L.G.A |  | 5 | Budget approval, Market Survey, warehouse, release of fund | 9 | 38 | PMT, Finance | 15200000
Procurement and Transportation Solar Panel for 9 L.G.A |  | 4 | Ditto | 9 |  | PMT, Finance | 101490000
Procurement of PV Structure Materials for 4 L.G.A |  | 5 | Ditto | 9 |  | PMT, Finance | 27300000
Procurement of AC & DC Cables and accessories for Mini-Grid for 4 L.G.A |  | 4 | Ditto | 9 |  | PMT, Finance | 0
Procurement of 4 X 35mm2 XLPE Cable for 4 .L.G.A |  | 4 | Ditto | 9 |  | PMT, Finance | 9880000
Procurement of new galvanized pole materials for four L.G.A (Kiyawa, Taura, Auyo & Kafin Hausa) and store in the Dutse Ware House |  | 5 | Ditto | 9 |  | PMT, Finance | 6720000
Procurement of paint and materials for the modification of existing poles |  | 5 | Ditto | 9 |  | PMT, Finance | 40430000
Procurement of Internet router and Six Month Data |  | 5 | Ditto | 9 |  | PMT, Finance | 1880000
procurement of materials for construction of container power house for Mini-Grid, including 1.5HP Inverter A.C |  | 5 | Ditto | 9 |  | PMT, Finance | 18280000
Schedule visit to China for FAT | Engr. Kadiri and Engr Joshua will visit China for FAT | 7 | 95% completion of production, VISA | 10 | 46 | Funds for Tickets | 12000000
Fabrication of Streetlight poles & Sign Board, for IESL office, and 4 L.G.A | Release work order to sub contractors | 6 | Sample fabrication | 10 |  | Sub contractor | 0
Construction of Pre-cast concrete Base for All in One | Release work order to sub contractors | 6 | Sample Pre cast | 10 |  | Sub contractor | 0
Site clearing and leveling, first four L.G.A |  | 3 | Survey report, Budget Approval, Site handover | 11 | 54 | PMT, Sub- contractor | 4000000
Wire fencing poles casting and installation of wire net, gate and rezor wire |  | 5 | Approval of budget, Procurement of material, Site Survey , Site Clearing | 11 |  | PMT, Sub- contractor | 5600000
Fibracation and installation of PV structure and Lighting arrestor at site |  | 7 | Approval of budget, Procurement of material, installation of wire net | 11 |  | PMT, Sub- contractor | 14700000
BESS container base, setting out, casting and curing |  | 5 | Approval of budget, Procurement of material, installation of wire net | 11 |  | PMT, Sub- contractor | 400000
Retrofiting of LGA Secretariat wiring system |  | 5 | Completion of all mini-grid installation | 11 |  | PMT, Sub- contractor | 4000000
Installation of PV panels |  | 3 | PV structure fabrication | 12 | 58 | PMT, Sub- contractor | 6160000
Shipping and Bill of lading of All-in-One Streetlight to Apapa Port |  | 30 | Completion of All in one, FAT | 13 | 93 | OEM, PMT, Finance | 149100000
Shipping and Bill of lading of BESS to Apapa Port |  | 30 | Completion of BESS, FAT | 13 |  | OEM, PMT, Finance | 25280000
Procurement of Mercedes- Benz Bucket lifters |  | 7 | shipment of materials | 13 |  | OEM, PMT, Finance | 100070000
Clearing/ custom duity of All-in-One and transportation from Lagos Port to Dutse Ware house |  | 10 | Bill of lading | 14 | 107 | OEM, PMT, Finance | 135000000
Clearing/ custom duity of BESS and transportation from Lagos Port to Dutse Ware house |  | 12 | Bill of lading | 14 |  | OEM, PMT, Finance | 34000000
Submit invoice no 2 (N5.2B spent, 4 months) | prepare invoice with supporting documents. Invite client for material inspection | 5 | Pre approval of invoice by client | 15 | 113 | PM, Finance | 0
Approval and payment of 50% 2nd Milestone | Follow up by account receivable | 14 |  | 16 | 136 | PM, Client, Finance | 0
Daily materials requisition form by sub-contractor | Material release form will be sign by Sub-contractor, project Engineer and Project Manager and will be release by Store officer. The underlisted materials per pole are, Pre-tested All-in-One Solar Streetlight Unit in a pack inclung bolt & nut. Galvanizing repair paint, Sky bucket lifter, light Crane, Ladder, 2.5KVA generator | 20 | Material in storage | 16 |  | PMT, Sub contractor | 0
De-energize site | Take outtage from disco/ L.G.A staff for safe work | 20 | Daily material supply | 16 |  | Ditto | 36240000
Decommissioning Existing Streetlights | There will be a sub-team for only decoping of the existing streetlight fitting head, disconnected the breaker, remove the bulb head, cable breakers and isolate the power, remove the existing pole for modification | 20 | De-energize | 16 |  | Ditto | 0
Installation,Alignment and Function test of All-in-One | Coupling /Installation of All-in-One to new/ modified poles | 20 | Pre-modification of poles, Pre- Test of all in one | 16 |  | Ditto | 0
Re-Energize remaining poles |  | 20 | Successful Installation, looping of connection | 16 |  | Ditto | 0
Excavate, recover armord cables and back filled the earh |  | 20 |  | 16 |  | Ditto | 8700000
Transportation of recovered materials to Safe location | Pole filting and other materials recovered will be transported to a selected safe location waiting for collection to client store. | 20 | Daily Material inventory sign off | 16 |  | Ditto | 0
Modification of existing poles and painting | There will be a mobile welding team and a mobile workshop with generator for on the spot modification to save moving up and down. The welding integrety will be check by Project Manager of Project Engineer or person apported by the PM | 20 | Delivery of recovered poles | 16 |  | Ditto | 11300000
Recovery of Generator | Decomissioning of 100KVA generator, recovery of amord cables and other accessaries | 1 | Decommissioning of existing streetlight, De-energizing | 16 |  | Ditto | 5560000
Recovery of Transformers | Decomissioning of 500KVA Transformers, recovery of amord cables, lighten arrestor, D-Fuse and other accessaries | 1 | Decommissioning of existing streetlight, De-energizing | 16 |  | Ditto | 9110000
Transportation to Client central stores | Collection of all recovered materials and transportation to client central store | 1 | Daily Recovery of materials | 16 |  | Ditto | 5260000
Fabrication of container for Power house/BESS |  | 5 | Approval of budget, Procurement of material, installation of wire net | 16 |  | Ditto | 800000
Installation of BESS |  | 3 |  | 16 |  | Ditto | 4000000
Configuration of Mini-Grid and online monitoring |  | 2 | PV structure fabrication, Fabrication of container Power house | 16 |  | Ditto | 6920000
Connection of L.G.A Secretariate to Mini-Grid & Installation of 4 X 35mm2 XLPE Cable |  | 2 | Retrofiting of LGA secretariat | 16 |  | Ditto | 6000000
Testing of Mini-Grid system |  | 1 | All connections of mini-grid components | 16 |  | Ditto | 1440000
Trainig of Opertors |  | 1 | Testing | 16 |  | Ditto | 0
Technical Commissioning |  | 1 | Training of operators | 16 |  | Ditto | 0
Procurement of perimeter wire fence materials |  | 5 | Budget approval, Market Survey, Renting of warehouse | 17 | 142 | Ditto | 19000000
Procurement of PV Structure Materials |  | 5 | Budget approval, Market Survey, Renting of warehouse | 17 |  | Ditto | 34130000
Procurement of AC & DC Cables and accessories for Mini-Grid |  | 4 | Budget approval, Market Survey, Renting of warehouse | 17 |  | Ditto | 0
Procurement of 4 X 35mm2 XLPE Cable |  | 4 |  | 17 |  | Ditto | 12350000
Procurement of new galvanized pole materials and store in the Dutse Ware House |  | 5 | Budget approval, Market Survey, Renting of warehouse | 17 |  | Ditto | 26890000
Procurement of paint and materials for the modification of existing poles |  | 5 | Budget approval, Market Survey, Renting of warehouse | 17 |  | Ditto | 124940000
Procurement of Internet router and Six Month Data |  | 5 | Budget approval, Market Survey, Renting of warehouse | 17 |  | Ditto | 2350000
procurement of materials for construction of container power house for Mini-Grid, including 1.5HP Inverter A.C for five L.G.A |  | 5 |  | 17 |  | Ditto | 22850000
Fabrigation ofStreetlight poles & Sign Board, for IESL office, and 4 L.G.A |  | 8 |  | 18 | 151 | Ditto | 4880000
Construction of Pre-cast concrete Base for All in One |  | 8 |  | 18 |  | Ditto | 7690000
Site clearing and leveling, first four L.G.A |  | 3 | Survey report, Budget Approval, Site handover | 18 |  | Ditto | 4000000
Wire fencing poles casting and installation of wire net, gate and rezor wire |  | 3 | Approval of budget, Procurement of material, Site Survey , Site Clearing | 19 | 155 | Ditto | 5600000
Fibracation and installation of PV structure and Lighting arrestor at site |  | 7 | Approval of budget, Procurement of material, installation of wire net | 20 | 163 | Ditto | 14700000
BESS container base, setting out casting and curing |  | 5 | Approval of budget, Procurement of material, installation of wire net | 20 |  | Ditto | 400000
Installation of PV panels |  | 3 | PV structure fabrication | 21 | 215 | Ditto | 6160000
Retrofiting of LGA Secretariat wiring system |  | 5 | Completion of all mini-grid installation | 21 |  | Ditto | 4000000
Daily materials requisition form by sub-contractor | Material release form will be sign by Sub-contractor, project Engineer and Project Manager and will be release by Store officer. The underlisted materials per pole are, Pre-tested All-in-One Solar Streetlight Unit in a pack inclung bolt & nut. Galvanizing repair paint, Sky bucket lifter, light Crane, Ladder, 2.5KVA generator | 45 | Material in storage | 21 |  | Execution, Team | 0
De-energize site | Take outtage from disco/ L.G.A staff for safe work | 45 | Daily material supply | 21 |  | Execution, Team | 93430000
Decommissioning Existing Streetlights | There will be a sub-team for only decoping of the existing streetlight fitting head, disconnected the breaker, remove the bulb head, cable breakers and isolate the power, remove the existing pole for modification | 45 | De-energize | 21 |  | Execution, Team | 0
Installation, Alignment and Function test of All-in-One | Coupling /Installation of All-in-One to new/ modified poles | 45 | Pre-modification of poles, Pre- Test of all in one | 21 |  | Execution, Team | 0
Re-Energize remaining poles |  | 45 | Successful Installation, looping of connection | 21 |  | Execution, Team | 0
Excavate, recover armord cables and back filled the earh |  | 20 |  | 21 |  | Execution, Team | 27520000
Transportation of recovered materials to Safe location | Pole filting and other materials recovered will be transported to a selected safe location waiting for collection to client store. | 45 | Daily Material inventory sign off | 21 |  | Execution, Team | 0
Modification of existing poles and painting | There will be a mobile welding team and a mobile workshop with generator for on the spot modification to save moving up and down. The welding integrety will be check by Project Manager of Project Engineer or person apported by the PM | 45 | Delivery of recovered poles | 21 |  | Execution, Team | 28970000
Recovery of Generator | Decomissioning of 100KVA generator, recovery of amord cables and other accessaries | 7 | Decommissioning of existing streetlight, De-energizing | 21 |  | Execution, Team | 11110000
Recovery of Transformers | Decomissioning of 500KVA Transformers, recovery of amord cables, lighten arrestor, D-Fuse and other accessaries | 7 | Decommissioning of existing streetlight, De-energizing | 21 |  | Execution, Team | 18230000
Transportation to Client central stores | Collection of all recovered materials and transportation to client central store | 2 | Daily Recovery of materials | 21 |  | Execution, Team | 9310000
Fabrication container for Power house/BESS |  | 5 | Approval of budget, Procurement of material, installation of wire net | 21 |  | Execution, Team | 800000
Installation of BESS |  | 3 |  | 21 |  | Execution, Team | 4000000
Configuration of Mini-Grid and online monitoring |  | 2 | PV structure fabrication, Fabrication of container Power house | 21 |  | Execution, Team | 6920000
Connection of L.G.A Secretariate to Mini-Grid & Installation of 4 X 35mm2 XLPE Cable |  | 2 | Retrofiting of LGA secretariat | 21 |  | Execution, Team | 6000000
Testing of Mini-Grid system |  | 1 | All connections of mini-grid components | 21 |  | Execution, Team | 1440000
Trainig of Opertors |  | 1 | Testing | 21 |  | Execution, Team | 0
Technical Commissioning |  | 1 | Training of operators | 21 |  | Execution, Team | 0
Progress invoice no 2 |  | 0 |  | 21 |  | PM, Finance | 0
Project Manager to email finance for 3rd Milestone Payments for Lot-1 and Lot-2 | IESL Finance department to prepare 3rd Milestone invoicess for Lot-1 And Lot 2 Projects | 1 |  | 21 |  | PM, Finance | 0
Preparation and submission of 3rd Milestone payment of LOT 1 and LOT 2 by finance |  | 2 |  | 21 |  | PM, Finance | 0
Approval and payment of 10% 2nd Milestone |  | 14 |  | 21 |  | Client, PM, Finance | 0
Fabrication of Sign Board |  | 3 |  | 22 | 225 | Execution, Team | 350000
Construction of Pre-cast concrete Base for All in One |  | 8 |  | 22 |  | Execution, Team | 4300000
Site clearing and leveling |  | 3 | Survey report, Budget Approval, Site handover | 22 |  | Execution, Team | 1000000
Wire fencing poles casting and installation of wire net, gate and rezor wire |  | 3 | Approval of budget, Procurement of material, Site Survey , Site Clearing | 23 | 228 | Execution, Team | 1400000
Fibracation and installation of PV structure and Lighting arrestor at site |  | 7 | Approval of budget, Procurement of material, installation of wire net | 24 | 236 | Execution, Team | 3680000
BESS container base casting and curing |  | 5 | Approval of budget, Procurement of material, installation of wire net | 24 |  | Execution, Team | 100000
Installation of PV panels |  | 3 | PV structure fabrication | 25 | 242 | Execution, Team | 1540000
Retrofiting of LGA Secretariat wiring system |  | 5 | Completion of all mini-grid installation | 25 |  | Execution, Team | 1000000
Daily materials requisition form by sub-contractor | Material release form will be sign by Sub-contractor, project Engineer and Project Manager and will be release by Store officer. The underlisted materials per pole are, Pre-tested All-in-One Solar Streetlight Unit in a pack inclung bolt & nut. Galvanizing repair paint, Sky bucket lifter, light Crane, Ladder, 2.5KVA generator | 20 | Material in storage | 26 | 266 | Execution, Team | 0
De-energize site | Take outtage from disco/ L.G.A staff for safe work | 20 | Daily material supply | 26 |  | Execution, Team | 19050000
Decommissioning Existing Streetlights | There will be a sub-team for only decoping of the existing streetlight fitting head, disconnected the breaker, remove the bulb head, cable breakers and isolate the power, remove the existing pole for modification | 20 | De-energize | 26 |  | Execution, Team | 0
Installation,Alignment and Function test of All-in-One | Coupling /Installation of All-in-One to new/ modified poles | 20 | Pre-modification of poles, Pre- Test of all in one | 26 |  | Execution, Team | 0
Re-Energize remaining poles |  | 20 | Successful Installation, looping of connection | 26 |  | Execution, Team | 0
Excavate, recover armord cables and back filled the earh |  | 20 |  | 26 |  | Execution, Team | 5010000
Transportation of recovered materials to Safe location | Pole filting and other materials recovered will be transported to a selected safe location waiting for collection to client store. | 20 | Daily Material inventory sign off | 26 |  | Execution, Team | 0
Modification of existing poles and painting | There will be a mobile welding team and a mobile workshop with generator for on the spot modification to save moving up and down. The welding integrety will be check by Project Manager of Project Engineer or person apported by the PM | 20 | Delivery of recovered poles | 26 |  | Execution, Team | 6030000
Recovery of Generator | Decomissioning of 100KVA generator, recovery of amord cables and other accessaries | 7 | Decommissioning of existing streetlight, De-energizing | 26 |  | Execution, Team | 2380000
Recovery of Transformers | Decomissioning of 500KVA Transformers, recovery of amord cables, lighten arrestor, D-Fuse and other accessaries | 7 | Decommissioning of existing streetlight, De-energizing | 26 |  | Execution, Team | 3910000
Transportation to Client central stores | Collection of all recovered materials and transportation to client central store | 2 | Daily Recovery of materials | 26 |  | Execution, Team | 1760000
Fabrication container for Power house/BESS |  | 5 | Approval of budget, Procurement of material, installation of wire net | 26 |  | Execution, Team | 200000
Configuration of Mini-Grid and online monitoring |  | 2 |  | 26 |  |  | 1730000
Connection of L.G.A Secretariate to Mini-Grid & Installation of 4 X 35mm2 XLPE Cable |  | 2 | Retrofiting of LGA secretariat | 26 |  | Execution, Team | 1500000
Testing of Mini-Grid system |  | 1 | All connections of mini-grid components | 26 |  | Execution, Team | 360000
Trainig of Opertors |  | 1 | Testing | 26 |  | Execution, Team | 0
Technical Commissioning |  | 1 | Training of operators | 26 |  | Execution, Team | 0
Submit invoice no 3 (N5.8B spent, 9 months spent, 7.2B due, additional N800m retention after 3 months) |  | 0 |  | 26 |  | PM, Finance | 0
Project Manager to email finance for 3rd Milestone Payments for Lot-1 and Lot-2 | IESL Finance department to prepare 3rd Milestone invoicess for Lot-1 And Lot 2 Projects | 1 |  | 26 |  | PM, Finance | 0
Preparation and submission of 3rd Milestone payment of LOT 1 and LOT 2 by finance |  | 2 |  | 26 |  | PM, Finance | 0
Miscellaneous (5%) |  | 14 |  | 26 |  | Client, PM, Finance | 285000000
[6 empty] | Total: | 5964600000